## BacklogSprint2
Sprint | ID | Item Type | Role/Layer | Title | Notes | Assigned | Priority | Status
2 | 1 | Backlog | Employee | Allow hotel employee users to log in |  |  | Required | Incomplete
|  | Task | Database | Stored Procedures to allow an employee to login and logout |  | Arik/Daniel
|  | Task | Data Access | Accessor Methods to allow employee log in |  | Arik/Daniel
|  | Task | Business Logic | UserManager Methods to allow employee login |  | Arik/Daniel
|  | Task | Presentation | User Login UI |  | Arik/Daniel
2 | 2 | Backlog | Employee | Allow user to view & update employee information |  |  | Required | Incomplete
|  | Task | Database | Stored Procedures to update an employee |  | Rose/Miguel
|  | Task | Database | Stored Procedures to archive an employee |  | Rose/Miguel
|  | Task | Data Access | Accessor Methods to update an employee |  | Rose/Miguel
|  | Task | Data Access | Accessor Methods to archive an employee |  | Rose/Miguel
|  | Task | Business Logic | EmployeeManager Methods to update an employee |  | Rose/Miguel
|  | Task | Business Logic | EmployeeManager Methods to archive an employee |  | Rose/Miguel
|  | Task | Presentation | Modify UI to include view and update of one employee |  | Rose/Miguel
|  | Task | Common | Update Employee Roles to an enumeration |  | Miguel |  | Done
|  | Task | Common | Employee needs a constructor |  | Rose/Miguel
|  | Task | Presentation | Add input mask for passwords |  | Rose/Miguel
|  | Task | Presentation | Add column sorts for list view |  | Rose/Miguel
2 | 2 | Backlog | Employee | Allow user to view & update Hotel Guest information |  |  | Required | Incomplete
|  | Task | Database | Stored Procedures to update a Hotel Guest |  | Rose/Miguel
|  | Task | Database | Stored Procedures to archive a Hotel Guest |  | Rose/Miguel
|  | Task | Data Access | Accessor Methods to update a Hotel Guest |  | Rose/Miguel
|  | Task | Data Access | Accessor Methods to archive a Hotel Guest |  | Rose/Miguel
|  | Task | Business Logic | HotelGuestManager Methods to update a Hotel Guest |  | Rose/Miguel
|  | Task | Business Logic | HotelGuestManager Methods to Archive a Hotel Guest |  | Rose/Miguel
|  | Task | Presentation | Modify UI to View & Update a Single Hotel Guest's information |  | Rose/Miguel
|  | Task | Presentation | Modify UI to archive Hotel Guest information |  | Rose/Miguel
|  | Task | Presentation | Add column sorts for list view |  | Rose/Miguel
|  | Task | Presentation | Add input mask for phone number |  | Rose/Miguel
|  | Task | Presentation | Add Update button to list screen to bring up edit UI |  | Rose/Miguel
2 | 2 | Backlog | Employee | Allow user to view, update and cancel bookings |  |  | Required | Incomplete
|  | Task | Database | Stored Procedure to update a Booking |  | Ryan
|  | Task | Data Access | Accessor Methods to update a Booking |  | Ryan
|  | Task | Business Logic | BookingManager Methods to update a booking |  | Tony/Ryan
|  | Task | Presentation | Modify UI to View & Update a single booking |  | Tony/Ryan
|  | Task | Common | Change Booking Object to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Database | Stored Procedure to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Data Access | Update Accessor to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Business Logic | Update BookingManager to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Presentation | Add Update button to list screen to bring up edit UI |  | Tony/Ryan
|  | Task | Presentation | Update Stored Procedure to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Presentation | Add column sorts for list view |  | Tony/Ryan
|  | Task | ? | Utilize User login information when booking a guest for an event |  | Tony/Ryan
|  | Task | Presentation | Change Guest field to a search box |  | Tony/Ryan
2 | 3 | Backlog | Employee | Add booking items to an invoice |  |  | Required | Incomplete
|  |  | Database | Stored Procedures to create an invoice when a Hotel Guest is added
|  |  | Data Access | Accessor to add an invoice
|  |  | Business Logic | Invoice Manager for adding booking line items
|  |  | Presentation | UI to view bookings for a hotel guest
|  |  | Common | Invoice Object

## BacklogSprint1
Sprint | ID | Item Type | Role/Layer | Title | Notes | Assigned | Priority | Status
1 | 1 | Backlog | Admin | Add an employee user with a role. |  |  | Required | Incomplete
| 1 | Task | Database | SQL to Create Employee table |  | Ryan |  | Updating with user fields
| 1 | Task | Database | Stored Procedures for Employee | Add, Get, GetList, Update, Selects as needed | Ryan |  | Updating with user fields
| 1 | Task | Business Objects | Add Employee Class |  | Ryan |  | Updating with user fields
| 1 | Task | Data Access | Add Employee Accessor |  | Ryan |  | Updating with user fields
| 1 | Task | Business Logic | Add EmployeeManager Class |  | Ryan |  | Updating with user fields
| 1 | Task | Presentation | Main Window UI |  | Pat
| 1 | Task | Presentation | Add Employee UI |  | Pat
| 1 | Task | Presentation | View Employee List | User Control Form added | Pat
| 1 | Task | Presentation | User Login - on main window | Add information so a given user level will have access to tabs | Arik
| 1 | Task | Database | Test data for employees |  | Rose
1 | 2 | Backlog | Employee | Add guests to an event. |  |  | Required | Incomplete
| 2 | Task | Database | SQL to create Booking Table |  | Tony |  | updating with Booking Line item fields
| 2 | Task | Database | SQL to create HotelGuest Table |  | Miguel |  | Can delete Hotel Guest PIN
| 2 | Task | Database | SQL to create Zip Code Table |  | Daniel |  | done
| 2 | Task | Database | Stored Procedures for Booking | Add, Get, GetList, Update, Selects as needed | Tony |  | updating with Booking Line item fields
| 2 | Task | Database | Stored Procedures for Hotel Guest | Add, Get, GetList, Update, Selects as needed | Miguel |  | done
| 2 | Task | Database | Stored Procedures for Zip Code Table | Add, Get, GetList, Update, Selects as needed | Daniel |  | done
| 2 | Task | Business Objects | Add Booking Class |  | Tony |  | updating with Booking Line item fields
| 2 | Task | Business Objects | Add Hotel Guest Object |  | Miguel |  | ready for testing
| 2 | Task | Data Access | Hotel Guest Accessor |  | Miguel |  | ready for testing
| 2 | Task | Data Access | Booking Accessor |  | Tony |  | updating with Booking Line item fields
| 2 | Task | Business Logic | Add Booking Manager Class |  | Tony |  | updating with Booking Line item fields
| 2 | Task | Database | Test data for Hotel Guest |  | Rose
| 2 | Task | Database | Test data for Bookings
| 2 | Task | Presentation | Add Booking UI |  | Tony
| 2 | Task | Presentation | View Booking List | User Control Form added
| 2 | Task | Presentation | Add Hotel Guest UI |  | Miguel
| 2 | Task | Presentation | View List of Hotel Guests UI | User Control Form added | Daniel
| 2 | Task | Database | Test data for Zip Code |  | Daniel
For all tables, make sure to create all stored procedures that go with them.
Sprint 2
|  | Task | Presentation | View/Update Single Hotel Guest UI
|  | Task | Presentation | View/Update Single Booking UI
|  | Task | Presentation | View/Update Single Employee UI
|  | Task | Business Objects | Employee Roles | may be enumeration | Arik

## Archive items
Sprint | ID | Item Type | Role/Layer | Title | Notes | Assigned | Priority | Status
1 | 1 | Backlog | Admin | Add an employee user with a role. |  |  | Required | Incomplete
|  | Task | Database | SQL to Create a User Login Table |  | Rose |  | Need to add archive field
|  | Task | Database | Stored Procedures for UserLogin | Add, Get, GetList, Update, Selects as needed | Rose |  | update per addition of archive field
|  | Task | Business Objects | Add UserLogin Class |  | Rose |  | Need to add archive field
|  | Task | Data Access | Add User Login Accessor |  | Rose |  | ready for testing
|  | Task | Business Logic | Add UserManager Class |  | Pat
|  | Task | Presentation | Add User UI |  | Arik
|  | Task | Presentation | Update User UI |  | Arik
|  | Task | Presentation | View User List | User Control Form added | Arik
1 | 2 | Backlog | Employee | Add guests to an event. |  |  | Required | Incomplete
|  | Task | Database | SQL to create Booking line Item Table |  | Arik |  | Need to add to VS and upload to GIT - right click on Event Database in VS2013 and select import.
|  | Task | Database | Stored Procedures for Booking Line Item | Add, Get, GetList, Update, Selects as needed | Arik |  | Need to add to VS and upload to GIT - right click on Event Database in VS2013 and select import.
|  | Task | Business Objects | Add Booking Line Item Class | Inherits from Booking Class | Arik |  | Need to look at inheritance with Booking
|  | Task | Data Access | Booking Line Item Accessor |  | Arik |  | ready for testing
|  | Task | Business Logic | BookingManager - line items |  | Arik
For all tables, make sure to create all stored procedures that go with them.