## BacklogFinalSprint
Sprint | ID | Item Type | Role/Layer | Title | Notes | Assigned | Priority | Status
4 |  | Backlog |  | Additional Features |  |  |  | Incomplete
|  |  | WPF | Develop a printable report for hotel guests with a list of paid events/fees. |  | Pat | Due 4/24
|  |  | WPF | Administrative control (WPF) for Event Types - Add/Edit/Archive |  | Miguel Pat | Due 4/24
|  |  | WPF/Website | XML reports for accounting and for each suppleir |  | Arik Justin | Due 4/24
|  |  | Website | Supplier needs to be able to update their password |  | Matt | Due 4/24
|  |  | Website | Printable report for suppliers to see who is signed up for an event |  | Matt Will | Due 4/24
|  |  | Website | Printable report for suppliers to see their sales data |  | Matt Will | Due 4/24
4 |  |  |  | Polish/Userability |  |  |  | Incomplete
|  |  | Website | Jquery Constraints on user data |  | Matt
|  |  | Website | Update titles on Supplier Screens | Change Listed Events to Events you Offer Change other title to Events you are hosting | Matt
|  |  | Website | Clickable headers for sorting capability |  | Matt
|  |  | Website/WPF | Restrict Start Date to before End Date only |  | Pat
|  |  | Website/WPF | Data Caching for Zip Code |  | Pat
|  |  | Guest Website | Add confirmation box for guest booking | I agree to pay $x for the event xxx on xxx and charge to my credit card on file. | Pat
|  |  | WPF | Generate a random 5 digit pin for the guests |  | Pat
|  |  | WPF | Update the inserts to reflect accurate bookings so numbers match |  | Pat
4 |  |  |  | Documentation |  |  |  | Incomplete
|  |  |  | Take out information on product |  | Rose Justin
|  |  |  | Class Diagrams should match the classes in program |  | Rose Justin
|  |  |  | Update Data Dictionary |  | Rose Justin
|  |  |  | Update all Google Drive Documents |  | Rose Justin
|  | Backlog | n/a | UserTesting |  |  |  | Incomplete
|  |  | Website | Develop test cases and fill out to document the testing | If issue cannot be fixed in 5 min or less, file an issue on GitHub | Kelsey
|  |  | WPF | Develop test cases and fill out to document the testing | If issue cannot be fixed in 5 min or less, file an issue on GitHub | Daniel
|  |  | Website | Develop test cases and fill out to document the testing | If issue cannot be fixed in 5 min or less, file an issue on GitHub | Reece
|  |  | WPF | Develop test cases and fill out to document the testing | If issue cannot be fixed in 5 min or less, file an issue on GitHub | Ryan
|  |  | Website | Fix Website Issues from UserTesting |  | Matt
|  |  | WPF | Fix WPF Issues from User Testing |  | Pat
|  | Backlog | n/a | Finish unit testing |  |  |  | Incomplete
Tony
Hunter
Bryan
|  | Backlog | n/a | Ensure Comments are in the standardized format |  |  |  | Incomplete
|  |  |  | All Methods/Classes |  | Tyler

## BacklogSprint3
Sprint | ID | Item Type | Role/Layer | Title | Notes | Assigned | Priority | Status
3 | 1 | Backlog | Vendor | A vendor will be able to sign in via the website. |  |  |  | Complete
|  | Task | Database | Add Vendor Login Table to the database |  | Rose |  | done
|  | Task | Database | Add Stored procedures for vendor log in | Add, Get and Archive | Rose |  | done
|  | Task | Data Access | Add LoginVendor Methods |  | Rose |  | done
|  | Task | Business Logic | Add LoginVendor Methods |  | Rose |  | done
|  | Task | Database | Add inserts statements to post-deployment script |  | Rose |  | done
3 | 2 | Backlog | Manager | A Hotel Employee will approve or deny a vendor application |  |  |  | Incomplete
|  | Task | Presentation | Add Button to the supplier tab to view the list of pending supplier approvals |  | Miguel |  | Done
|  | Task | Presentation | Create skeleton form for list of pending supplier approvals |  | Miguel |  | Done
|  | Task | Presentation | Create skeleton form for individual supplier approval |  | Miguel |  | Done
|  | Task | Presentation Business logic Data Access | List view of pending applications | List needs to refresh after changes. Comments need added | Ryan
|  | Task | Presentation Business logic Data Access | View/approve detailed Pending application form | UI needs some updates for user interaction | Ryan/Pat
|  | Task | Presentation Business logic Data Access | Assign a newly approved vendor a default password | Default is Password#1 Matt will work on change password Done in the creation of new records for user login table | Rose |  | Done
|  | Task | Presentation Business logic Data Access | Assign a newly approved vendor a username |  | Ryan/Pat |  | Done
|  | Task | Presentation Business logic Data Access | Include a field to record the negotiated % for vendor sales |  | Ryan |  | Done
3 | 3 | Backlog | Employee | A Hotel Employee will be able to assign a PIN number to Hotel Guest to allow him/her the ability to sign up for event listings |  |  |  | Incomplete
|  |  | Presentation Business logic Data Access | Update Hotel Guest UI to add a pin at guest checkin |  | Pat |  | Done
|  |  | Data Access | At guest checkout - clear the pin |  | TBD
3 | 4 | Backlog | Hotel Guest | A Hotel Guest will have the ability to sign up for event listings via hotel website |  |  |  | Incomplete
|  | Task | Presentation Business logic Data Access | Develop a web ui for viewing of available event listings | JQuery on website for validation and restricted controls (spinner) | Pat
|  | Task | Presentation Business logic Data Access | Add the booking when the guest types in the assigned pin |  | Pat
3 | 5 | Backlog | Employee | A hotel employee will have a printable report of events attended to accompany guest bill at checkout |  |  |  | Incomplete
|  |  |  | Develop a printable report for hotel guests with a list of paid events/fees. |  | Arik
3 | 6 | Backlog | n/a | Ensure the appropriate logic is in the BLL |  |  |  | Incomplete
|  |  | Presentation Business logic | Employee UI |  | Tony |  | Done
|  |  | Presentation Business logic | Hotel Guest |  | Tony |  | Done
|  |  | Presentation Business logic | Invoice |  | Pat |  | Done
|  |  | Presentation Business logic | Booking |  | Pat |  | Done
|  |  | Presentation Business logic | Supplier Application Supplier (as needed) |  | Pat |  | Done
3 | 7 | Backlog | n/a | Add Data Caching to BLL |  |  |  | Incomplete
|  |  | Business logic | Booking methods | These are the only ones we need for web use | Pat |  | Done
3 | 8 | Backlog | n/a | Develop Unit Tests for BLL and Accessor methods |  |  |  | Incomplete
|  |  | Business Logic | Booking Manager Methods | Develop test methods for BLL | Tony
|  |  | Business Logic | Invoice Manager Methods | Develop test methods for BLL | Rose
|  |  | Business Logic | Employee Manager Methods | Develop test methods for BLL | Tony
|  |  | Business logic | SupplierLogin Manager Methods | Develop test methods for BLL | Rose |  | done
|  |  | Business Logic | Hotel Guest Manager Methods | Develop test methods for BLL | Rose
|  |  | Data Access | Booking Accessor Methods | Develop test methods for Data Access Layer | Tony
|  |  | Data Access | Invoice Accessor Methods | Develop test methods for Data Access Layer | Rose
|  |  | Data Access | SupplierLogin Accessor Methods | Develop test methods for Data Access Layer | Rose |  | done
|  |  | Data Access | Employee Accessor Methods | Develop test methods for Data Access Layer | Tony
|  |  | Data Access | Hotel Guest Accessor Methods | Develop test methods for Data Access Layer | Rose |  | done
3 | 9 | Backlog | n/a | Ensure Comments are in the standardized format |  |  |  | Incomplete
|  |  | Presentation Business logic Data Access Objects | Booking |  | Daniel
|  |  | Presentation Business logic Data Access Objects | Invoice |  | Daniel
|  |  | Presentation Business logic Data Access Objects | Hotel Guest |  | Daniel
|  |  | Presentation Business logic Data Access Objects | Employee |  | Daniel
3 | 10 | Backlog | n/a | UI Improvements |  |  |  | Incomplete
|  |  |  | Double click on record in a list view to view the detailed screen |  | Miguel
|  |  |  | DB Connection error on main window- fix it | One error message when db is not found | Miguel |  | Done
|  |  |  | right click for menu with options for edit etc |  | Miguel
|  |  |  | Add Search Box to each tab in main window |  | Justin |  | Done
NO LONGER NEEDED
|  |  | Business logic | LoginVendor methods - Data Caching
|  |  | Business logic | Employee methods- Data Caching
|  |  | Business logic | Hotel Guest methods- Data Caching
|  |  | Business logic | Invoice methods- Data Caching

## BacklogSprint2
Sprint | ID | Item Type | Role/Layer | Title | Notes | Assigned | Priority | Status
2 | 1 | Backlog | Employee | Allow hotel employee users to log in |  |  | Required | Incomplete
|  | Task | Database | Stored Procedures to allow an employee to login and logout |  | Arik/Daniel
|  | Task | Data Access | Accessor Methods to allow employee log in |  | Arik/Daniel
|  | Task | Business Logic | UserManager Methods to allow employee login |  | Arik/Daniel
|  | Task | Presentation | User Login UI | Built - needs tested | Arik
|  | Task | Presentation | Populate main window with tabs according to user level |  | Daniel
2 | 2 | Backlog | Employee | Allow user to view & update employee information |  |  | Required | Incomplete
|  | Task | Database | Stored Procedures to update an employee |  | Miguel
|  | Task | Database | Stored Procedures to archive an employee |  | Miguel |  | Done
|  | Task | Data Access | Accessor Methods to update an employee | password changes need addressed | Miguel
|  | Task | Data Access | Accessor Methods to archive an employee |  | Miguel |  | Done
|  | Task | Business Logic | EmployeeManager Methods to update an employee |  | Miguel |  | Done
|  | Task | Business Logic | EmployeeManager Methods to archive an employee |  | Miguel |  | Done
|  | Task | Presentation | Modify UI to include view and update of one employee |  | Miguel |  | Done
|  | Task | Common | Update Employee Roles to an enumeration |  | Miguel |  | Done
|  | Task | Presentation | Add input mask for passwords |  | Miguel
|  | Task | Presentation | Add verification field for passwords |  | Miguel
|  | Task | Presentation | Add column sorts for list view |  | Will Fritz
2 | 2 | Backlog | Employee | Allow user to view & update Hotel Guest information |  |  | Required | Incomplete
|  | Task | Database | Stored Procedures to update a Hotel Guest |  | Rose |  | done
|  | Task | Database | Stored Procedures to archive a Hotel Guest | Final implementation will move to Invoice a/o 2/27/15 | Rose |  | done
|  | Task | Data Access | Accessor Methods to update a Hotel Guest |  | Rose |  | done
|  | Task | Data Access | Accessor Methods to archive a Hotel Guest | parameters not wanting to be placed in the stored procedure Moved to Invoice | Rose |  | n/a
|  | Task | Business Logic | HotelGuestManager Methods to update a Hotel Guest |  | Rose |  | done
|  | Task | Business Logic | HotelGuestManager Methods to Archive a Hotel Guest | Final implementation will move to Invoice a/o 2/27/15 | Rose |  | done
|  | Task | Presentation | Modify UI to View & Update a Single Hotel Guest's information | Final implementation will move to Invoice a/o 2/27/15 | Rose |  | done
|  | Task | Presentation | Modify UI to archive Hotel Guest information | Final implementation will move to Invoice a/o 2/27/15 | Rose
|  | Task | Presentation | Add column sorts for list view |  | Will Fritz
|  | Task | Presentation | Add input mask for phone number |  | Rose
|  | Task | Presentation | Add Update button to list screen to bring up edit UI | Final implementation will move to Invoice a/o 2/27/15 | Rose |  | done
|  | Task | Presentation | Change error label to message box |  | Rose
|  | Task | Presentation | Add Room # field to table, object and all stored procedures |  | Rose
2 | 2 | Backlog | Employee | Allow user to view, update and cancel bookings |  |  | Required | Incomplete
|  | Task | Database | Stored Procedure to update a Booking |  | Ryan
|  | Task | Data Access | Accessor Methods to update a Booking |  | Ryan
|  | Task | Business Logic | BookingManager Methods to update a booking |  | Tony/Ryan
|  | Task | Presentation | Create UI to Update/Cancel a single booking |  | Tony/Ryan
|  | Task | Common | Change Booking Object to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Database | Stored Procedure to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Data Access | Update Accessor to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Business Logic | Update BookingManager to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Presentation | Add Update button to list screen to bring up edit UI | incorporating on View Guest/Invoice as of 2/27/15 | Tony/Ryan
|  | Task | Presentation | Update Stored Procedure to accommodate refund & cancellation of a booking |  | Tony/Ryan
|  | Task | Presentation | Add column sorts for list view | No list view as of 2/27/15 | Will Fritz
|  | Task | ? | Utilize User login information when booking a guest for an event |  | Tony/Ryan
|  | Task | Presentation | Change Guest field to a search box | No longer needed on that form as of 2/27/15 | Tony/Ryan
2 | 3 | Backlog | Employee | Add booking items to an invoice |  |  | Required | Incomplete
|  | Task | Common | Create an Invoice Object |  | Pat |  | Done
|  | Task | Database | Create Stored Procedures to view a guest's invoice |  | Pat
|  | Task | Database | Stored Procedures to create an invoice when a Hotel Guest is added |  | Pat
|  | Task | Database | Stored Procedures to archive invoice, bookings and guest when a Hotel Guest checks out |  | Pat
|  | Task | Data Access | Create Accessor Methods to view a guest's invoice |  | Pat |  | Done
|  | Task | Data Access | Create Accessor Methods to add an invoice |  | Pat
|  | Task | Data Access | Create Accessor Methods to close/archive an invoice, booking and hotel guest |  | Pat
|  | Task | Business Logic | Create Invoice Manager methods to view a guest's booking line items |  | Pat |  | Done
|  | Task | Business Logic | Create Invoice Manager methods for Closing an invoice |  | Pat
|  | Task | Presentation | Create UI to view a guest's invoice |  | Pat |  | Done
|  | Task | Presentation | Create UI List view of open invoices | Using Hotel Guest tab a/o 2/27/15 | Pat
2 | 6 | Backlog |  | General Improvements |  |  | Optional | Incomplete
|  |  |  | Uniform Window Enhancements |  | Miguel
Search Box
One error message when db is not found
Double clicks on list windows to bring up view form

## BacklogSprint1
Sprint | ID | Item Type | Role/Layer | Title | Notes | Assigned | Priority | Status
1 | 1 | Backlog | Admin | Add an employee user with a role. |  |  | Required | Incomplete
| 1 | Task | Database | SQL to Create Employee table |  | Ryan |  | Updating with user fields
| 1 | Task | Database | Stored Procedures for Employee | Add, Get, GetList, Update, Selects as needed | Ryan |  | Updating with user fields
| 1 | Task | Business Objects | Add Employee Class |  | Ryan |  | Updating with user fields
| 1 | Task | Data Access | Add Employee Accessor |  | Ryan |  | Updating with user fields
| 1 | Task | Business Logic | Add EmployeeManager Class |  | Ryan |  | Updating with user fields
| 1 | Task | Presentation | Main Window UI |  | Pat
| 1 | Task | Presentation | Add Employee UI |  | Pat
| 1 | Task | Presentation | View Employee List | User Control Form added | Pat
| 1 | Task | Presentation | User Login - on main window | Add information so a given user level will have access to tabs | Arik
| 1 | Task | Database | Test data for employees |  | Rose
1 | 2 | Backlog | Employee | Add guests to an event. |  |  | Required | Incomplete
| 2 | Task | Database | SQL to create Booking Table |  | Tony |  | updating with Booking Line item fields
| 2 | Task | Database | SQL to create HotelGuest Table |  | Miguel |  | Can delete Hotel Guest PIN
| 2 | Task | Database | SQL to create Zip Code Table |  | Daniel |  | done
| 2 | Task | Database | Stored Procedures for Booking | Add, Get, GetList, Update, Selects as needed | Tony |  | updating with Booking Line item fields
| 2 | Task | Database | Stored Procedures for Hotel Guest | Add, Get, GetList, Update, Selects as needed | Miguel |  | done
| 2 | Task | Database | Stored Procedures for Zip Code Table | Add, Get, GetList, Update, Selects as needed | Daniel |  | done
| 2 | Task | Business Objects | Add Booking Class |  | Tony |  | updating with Booking Line item fields
| 2 | Task | Business Objects | Add Hotel Guest Object |  | Miguel |  | ready for testing
| 2 | Task | Data Access | Hotel Guest Accessor |  | Miguel |  | ready for testing
| 2 | Task | Data Access | Booking Accessor |  | Tony |  | updating with Booking Line item fields
| 2 | Task | Business Logic | Add Booking Manager Class |  | Tony |  | updating with Booking Line item fields
| 2 | Task | Database | Test data for Hotel Guest |  | Rose
| 2 | Task | Database | Test data for Bookings
| 2 | Task | Presentation | Add Booking UI |  | Tony
| 2 | Task | Presentation | View Booking List | User Control Form added
| 2 | Task | Presentation | Add Hotel Guest UI |  | Miguel
| 2 | Task | Presentation | View List of Hotel Guests UI | User Control Form added | Daniel
| 2 | Task | Database | Test data for Zip Code |  | Daniel
For all tables, make sure to create all stored procedures that go with them.
Sprint 2
|  | Task | Presentation | View/Update Single Hotel Guest UI
|  | Task | Presentation | View/Update Single Booking UI
|  | Task | Presentation | View/Update Single Employee UI
|  | Task | Business Objects | Employee Roles | may be enumeration | Arik

## Archive items
Sprint | ID | Item Type | Role/Layer | Title | Notes | Assigned | Priority | Status
1 | 1 | Backlog | Admin | Add an employee user with a role. |  |  | Required | Incomplete
|  | Task | Database | SQL to Create a User Login Table |  | Rose |  | Need to add archive field
|  | Task | Database | Stored Procedures for UserLogin | Add, Get, GetList, Update, Selects as needed | Rose |  | update per addition of archive field
|  | Task | Business Objects | Add UserLogin Class |  | Rose |  | Need to add archive field
|  | Task | Data Access | Add User Login Accessor |  | Rose |  | ready for testing
|  | Task | Business Logic | Add UserManager Class |  | Pat
|  | Task | Presentation | Add User UI |  | Arik
|  | Task | Presentation | Update User UI |  | Arik
|  | Task | Presentation | View User List | User Control Form added | Arik
1 | 2 | Backlog | Employee | Add guests to an event. |  |  | Required | Incomplete
|  | Task | Database | SQL to create Booking line Item Table |  | Arik |  | Need to add to VS and upload to GIT - right click on Event Database in VS2013 and select import.
|  | Task | Database | Stored Procedures for Booking Line Item | Add, Get, GetList, Update, Selects as needed | Arik |  | Need to add to VS and upload to GIT - right click on Event Database in VS2013 and select import.
|  | Task | Business Objects | Add Booking Line Item Class | Inherits from Booking Class | Arik |  | Need to look at inheritance with Booking
|  | Task | Data Access | Booking Line Item Accessor |  | Arik |  | ready for testing
|  | Task | Business Logic | BookingManager - line items |  | Arik
For all tables, make sure to create all stored procedures that go with them.